## Slide 1
Materiel Solution
Analysis
Materiel
Development
Decision
Materiel Solution Analysis
Purpose: Assess potential materiel solutions
Enter: Approved ICD and study guidance for conducting AoA.
Activities: Conduct AoA, develop Technology Development Strategy (TDS) & draft CDD
Guided by: ICD and AoA Plan
Exit: Materiel solution to capability need in ICD recommended by lead Component conducting AoA, and phase-specific exit criteria have been satisfied
New terms/requirements in blue
A
Notes: Point out requirements to enter and leave (exit) each phase
-Note the activities, and importance of JCIDS documents (ICD) to guide each phase.
-The enter and exit bullets on these charts are “generic” to all programs. Read about program specific “exit criteria” in the DAG.
Materiel Solution Analysis: The purpose of this phase is different from Concept Refinement (CR). The AoA during CR was conducted to “refine” the materiel solutions prioritized in the ICD. The ICD no longer does this, so the AoA is now focused on alternative solutions provided from a number of sources: “a diversified range of large and small businesses”.
Revisions to JCIDS: Because portions of the 5000.02, like the MSA phase, take into account upcoming changes to JCIDS, these changes should be pointed out.
-The Functional Solutions Analysis (FSA) part of the Capabilities-Based Assessment (CBA) has been eliminated.
-ICD will no longer contain a prioritized list of potential materiel alternatives. The ICD will define non-materiel options, DOTMLPF and policy changes that may lead to a Joint DCR. If non-materiel approaches are not sufficient to mitigate the warfighting capability gap, and a materiel solution is required, the ICD will make a recommendation on the type of materiel solution preferred: IT system, evolution of existing systems with significant capability improvement, or a transformational approach for “breakout” systems that differ significantly in form, function, operation and capabilities from existing systems and offer significant improvement over current capabilities or transform how the mission is accomplished.
-These materiel options will be investigated during the MSA phase during the AoA. Concurrent with the AoA, a draft CDD (see draft CJCSI 3170.01G) will be prepared to guide the TD phase activities.

## Slide 2
MDA approves:
  Materiel solution
  Technology Development Strategy (TDS)
  Exit criteria for next phase
  Milestone A Certification (10 USC 2366a)
  Acquisition Decision Memorandum (ADM)
Milestone A
Statutory & Regulatory Requirements
Acquisition Decision Memorandum (ADM)
Analysis of Alternatives (AoA)
Acquisition Information Assurance Strategy
Clinger-Cohen Act (CCA) Compliance
Clinger-Cohen Act Certification (MAIS)
CIO Confirmation of CCA Compliance for all non-MAIS IT
Consideration of Technology Issues
Component Cost Estimate (CCE)
Economic Analysis (MAIS)
Exit Criteria
Exit Criteria
Initial Capabilities Document (ICD)
Item Unique Identification (IUID) Implementation
Plan
Life Cycle Signature Support Plan
Market Research
MDA Program Certification
Program Protection Plan (PPP)
Systems Engineering Plan (SEP)
Technology Development Strategy (TDS)
Test & Evaluation Strategy (TES)
Milestone A
New terms/requirements in blue
Notes: -Materiel Solution: Previously, the term “preferred solution” was used to describe what the MDA approved at MS A. “Approved materiel solution” makes a clearer statement.
-Technology Development Strategy must be approved before release of final RFP for TD phase.
-Milestone A Certification, (MDA Program Certification) at Milestone A, is a statutory requirement (see backup slide). It is a signed MFR from the MDA; cannot be delegated.
-Component Cost Estimate (CCE): a new name for Component Cost Analysis (CCA)
-Item Unique Identification (IUID) Implementation Plan. DoDI 8320.04, requires unique IUID identifiers be established to enable items to be tracked and traced throughout their lifecycle
-Life Cycle Signature Support Plan. Signature. A distinctive basic characteristic or set of characteristics that consistently re-occurs and uniquely identifies a piece of equipment, activity, individual, or event. Life-Cycle Signature Support Plans. A management plan that is applied throughout the life of a signature-dependent acquisition that bases all programmatic decisions on the anticipated mission-related and economic benefits derived over the life of a signature-dependent acquisition. See DoDD 5250.01.
-Systems Engineering Plan. PM prepares a SEP for each milestone review, beginning with MS A. At MS A, the SEP supports the TDS; at MS B or later, the SEP supports the Acquisition Strategy. The SEP describes the program’s overall technical approach, including key technical risks, processes, resources, metrics, and applicable performance incentives. It also details the timing, conduct, and success criteria for technical reviews.

## Slide 3
Technology Development
Purpose: Reduce technology risk, Demonstrate Critical Technology on Prototypes, Complete Preliminary Design
Enter: MDA approved materiel solution and TDS; funding for TD phase activities
Activities: Competitive prototyping; Develop RAM strategy; conduct Preliminary Design Review (PDR)
Guided by: ICD & TDS and supported by SE planning
Exit: Affordable increment of military-useful capability identified; technology demonstrated in relevant environment; manufacturing risks identified; PDR conducted for candidate solutions; system or increment ready for production within short time frame (normally less than 5 years for weapon systems)
New terms/requirements in blue
Technology
Development
A
B
Notes: The blue bold items in italics highlight the emphasis on systems engineering in technology development.
Competitive Prototyping: Two or more competing teams producing prototypes of the system and/or key system elements.
RAM Strategy: Reliability, Availability, and Maintainability strategy that includes a reliability growth program is documented in the SEP, in the LCSP, and assessed during tech reviews, T&E and Program Support Reviews.
Preliminary Design Review (PDR).
-A PDR will be conducted for the candidate design(s) to establish the allocated baseline (hardware, software, human/support systems) and underlying architectures and to define a high-confidence design.
-A successful PDR informs requirements trades; improves cost estimates; and identifies remaining design, integration, and manufacturing risks.
-The PDR will be conducted at the system level and include user representatives and associated certification authorities.
-A PDR Report is provided to the MDA at Milestone B and includes recommended requirements trades based upon an assessment of cost, schedule, and performance risk.
-Note: The CDD KPPs and other performance attributes should reflect the trades from the PDR report; however, the CDD must be approved before MS B. The requirements trades recommended at MS B could be the “derived” technical requirements, not sure.

## Slide 4
MDA approves:
  Program Initiation (for most programs)
  Entry into EMD
  Acquisition Strategy
  Acquisition Program Baseline
  LRIP quantities
  Exit criteria for next phase
  Type of Contract
  Milestone B Certification (10 USC 2366b)
  ADM
Milestone A
Milestone B
New terms/requirements in blue
Notes: Program Initiation (not “new start”). Effort was a new start in PPBE when funding for MSA and TD phases were sought)
-Important: at MS B PM must demonstrate “full funding” in FYDP – i.e., at least 6 years of funding.
-PM was probably assigned prior to MS A – need someone in charge to get ready for MS A and B.
-Content of acq strategy is in DAG, Chapt. 2.
-Acq Strategy must be approved before release of final RFP for EMD.
-APB reflects KPPs, and other data for schedule and cost – all related to the CDD and to key programmatic activities (such as T&E)
-Certification required by Congress (see backup). Nothing in required certification not already required by 5000.02.
-Exit criteria is program specific (e.g., attain first flight prior to MS C).
-Type of contract: If MDAP and cost-type is chosen, needs written determination by MDA. DAG will have to address this. Waiting for MS B to get decision is no-go. Need contractor proposals in hand prior to MS B for obvious reasons.

## Slide 5
Engineering and Manufacturing Development
Engineering & Manufacturing Development
Purpose: Develop a system or increment of capability, develop an affordable manufacturing process, minimize logistics footprint
B
Integrated System Design
System Capability & Manufacturing Process Demonstration
Enter: Mature Technology; Approved Requirements; Full Funding in FYDP
Activities: Define System of System Functionality & Interfaces, Complete Detailed Design, System-Level PDR (as needed)/CDR, Establish Product Baseline,
Guided by: CDD, Acq Strategy, SEP & TEMP
Exit: Complete System-Level CDR and Post-CDR Assessments by MDA
Enter: Post-CDR Assessment and Establishment of initial Product Baseline
Activities: Developmental Testing (DT) Assesses Progress Against Technical Parameters, and Operational Assessments (OA) Against CDD
Guided by: CDD, Acq Strategy, SEP & TEMP
Exit: System Demonstrated in Intended Environment using production-representative articles; Manufacturing Processes Demonstrated; Meets Exit Criteria and MS C Entrance Requirements
New terms/requirements in blue
Post CDR
Assessment
Post PDR
Assessment
C
Notes: PDR conducted if not conducted prior to MS B. Applies to programs that enter at MS B, or if design changes occur during TD that require PDR after EMD contract award. PDR report provided by PM to MDA.
Post-PDR Assessment required if PDR conducted after MS B. Same rules as for pre-MS B PDR (see Technology Development chart), to include ADM.
Post CDR Assessment:
-System-Level CDR Conducted as soon as practicable after Program Initiation
-PM Provides a Post-CDR Report
-MDA Reviews the Post-CDR Report and the PM’s Plans to Resolve or Mitigate Issues/Risks
-Results of the Post-CDR Assessment are Documented in an ADM
Note use of Production-Representative articles. Previous 5000.2 said, “prototypes or EDMs”. Even though DAU defines EDMs as production representative, there is no DoD-level standard use of the term. The use of production-representative articles is particularly important for those programs that do not have LRIP and MS C is the production decision.

## Slide 6
Milestone A
Milestone C
MDA Approves:
  Updated Acquisition Strategy and Acquisition Program Baseline
  Entry into LRIP for systems that require a LRIP, into production or procurement for systems that do not require LRIP, or into limited deployment for MAIS programs or software intensive systems with no production components
  Exit criteria for LRIP if appropriate
  Acquisition Decision Memorandum
Notes: No change from 2003 DoDI 5000.02.

## Slide 7
Production & Deployment
Enter: Acceptable performance in DT & OA; mature software; no significant manufacturing risks; approved CPD; refined integrated architecture; acceptable interoperability and operational supportability; demonstration of affordability; fully funded; phased for rapid deployment.
Activities: IOT&E, LFT&E and Interoperability Testing of Production-Representative Articles; IOC possible
Guided by: CPD, TEMP
Exit: System Operationally Effective, Suitable and Ready for Full-Rate Production
Enter: Beyond LRIP & LFT&E Reports (OSD T&E/LFT&E programs) Submitted to Congress
Activities: Full-Rate Production; Fielding and Support of Fielded Systems; IOC/FOC
Guided by: Acq Strategy & Life Cycle Sustainment Plan
Exit: Full Operational Capability; Deployment Complete
Purpose: Achieve an operational Capability that satisfies mission needs
Production & Deployment
FRP
Decision
Review
LRIP/IOT&E
C
Full-Rate Production & Deployment
New terms/requirements in blue
Notes: Essentially same as the 2003 DoDI 5000.02.
Guided By: DoDI 5000.02 indicates what documents “guide” the phase activities for MSA, TD and EMD; however, it does not state what documents guide Production and Deployment. So, shown here some obvious documents that guide the activities.